## Defect Sheet
# | Module | Feedback Type | Severity | Priority | Description | Steps to Recreate | Reported By | Reported Date | Status | Resolved Date | Screenshot Reference | Resolution/Comments | Remark (IFQM) | IFQM Validation
KAL-001 | Platform Admin - Tenant Management | Bug | Critical | P1 | IFQM's own organisation database could not be reached by the backend. The Platform Admin dashboard showed IFQM as "ACTIVE" but flagged with a red "DB unreachable" label, and opening its detail page returned an HTTP 503 error ("Tenant database is unavailable"). Each organisation on the platform has its own separate database, and IFQM's own database was the one that couldn't be reached - this has since been fixed and re-verified as working. | 1. Log in to Kalpion as Platform Admin (platform@ifqm.io). 2. Click "Organisations" in the left menu. 3. Find the row for "IFQM" and look at the Status column. 4. Click the three-dot menu on that row and choose "View overview". 5. Before the fix: an error banner "Tenant database is unavailable" appeared instead of the organisation's details. | AI Automation Testing | 2026-09-11 | Fixed | 2026-09-16 |  | Vendor traced this to (1) the deploy process stripping out .sql files, including the file needed to set up a new organisation's database, and (2) the app's database user only having permission on the shared master database, not on individual organisation databases. Both were fixed and deployed; confirmed resolved on retest. | Recommend the vendor also confirm no other organisation was silently affected by the same missing database permission, since it could affect newly created organisations too, not just this one. | Accepted - verified fixed on 16-Sep-2026 (tenant detail page now returns a normal response instead of the 503 error).
KAL-002 | Platform Admin - Organisations (Create) | Bug | High | P1 | Creating a new organisation can fail with a raw database error if its name is long enough. The form auto-generates an "Organization Code" (URL slug) from the Organisation Name - for example, "IFQM QA Fresh Test" becomes "ifqm-qa-fresh-test" (19 characters) - and if that code is too long for the database column, submitting the form shows the user a confusing raw error (HTTP 500, MySQL code ER_DATA_TOO_LONG) instead of a clear message asking them to shorten it. Manually shortening the code works around it. | 1. Log in as Platform Admin. 2. Go to Organisations, click "+ New Organisation". 3. Type Organisation Name = "IFQM QA Fresh Test" (the code field auto-fills to "ifqm-qa-fresh-test"). 4. Fill in Admin Name, Admin Email, Admin Password. 5. Click "Create Organisation". 6. Error shown: "The organisation could not be created... Quote this when reporting it: ER_DATA_TOO_LONG." 7. To confirm the cause, manually shorten the Organization Code field to something short like "ifqmqa" and click Create Organisation again - this time it succeeds. | AI Automation Testing | 2026-09-17 | Fixed | 2026-09-23 |  | Root cause: the organisation's admin account is given an employee ID built as "<ORG CODE>-ADMIN", but the employee ID column only holds 20 characters while the code itself is allowed up to 30. Any code longer than 14 characters therefore overflowed the column, which the database reported as the raw ER_DATA_TOO_LONG error. The ID is now built to fit the column, shortening the code portion rather than the readable "-ADMIN" suffix. Retested with a 22-character code: the organisation is created normally and the admin ID fits. A regression test was added. | Recommend either limiting the auto-generated code to a safe length, validating it before submission with a clear message ("code too long, please shorten it"), or increasing the database column size - whichever best fits the intended design. | Pending
KAL-003 | Roles & Permissions - User Management | Bug | High | P2 | "Plant Head" appears twice in the role dropdown when adding or filtering users - but they're actually two different roles internally ("plant_head" and "executive") sharing the same mislabelled name. Only the Admin Panel's Hierarchy screen correctly shows the second one as "Executive". An admin can easily pick the wrong one, and that person then won't count as the real Plant Head for final idea approval, with no indication anything went wrong. | 1. Log in as an Organisation Admin. 2. Go to Admin Panel > User List. 3. Click the role filter dropdown at the top - "Plant Head" appears twice in a row. 4. Go to Admin Panel > User List > "+ Add User" and open the Role dropdown there - the same duplicate "Plant Head" appears. 5. Now go to Admin Panel > Hierarchy > "Add a stage..." dropdown - here the equivalent role is correctly labelled "Executive", proving the two entries are genuinely different roles that share one label everywhere else. | AI Automation Testing | 2026-09-17 | Fixed | 2026-09-23 |  | Confirmed as reported: two different roles ("plant_head" and "executive") were both labelled "Plant Head" in the interface, while the Hierarchy screen correctly showed the second as "Executive". This was a label error only; the two roles were always distinct internally. The "executive" label now reads "Executive" everywhere, in all seven languages. Retested on the Add User and role filter dropdowns: the duplicate is gone and the filter now reads Organisation Admin / Executive / Senior Manager / Manager / Team Lead / Employee. | This is a labelling bug, not just cosmetic - it can lead to real, silent role-assignment mistakes. Recommend fixing the label wherever the "executive" role is shown, so it reads "Executive" consistently everywhere. | Pending
KAL-004 | Platform Admin - Billing | Bug | Medium | P2 | The platform-wide Billing page's "Paying" summary tile always shows 0, even though several organisations in the table directly below it are clearly marked "Paid - X day(s) left." The summary tiles' totals also don't add up to the actual number of organisations on the platform, so the at-a-glance billing overview can't be trusted. | 1. Log in as Platform Admin. 2. Click "Billing" in the left menu. 3. Look at the summary tiles at the top: "Paying", "On trial", "Expiring soon", "Lapsed", "No plan set". 4. Note "Paying" reads 0. 5. Scroll to the organisations table below and find rows where the "Billing" column says "Paid - X day(s) left". 6. Confirm these paid organisations exist while the "Paying" tile still shows 0. | AI Automation Testing | 2026-09-16 | Fixed | 2026-09-23 | Captured via page text extraction on 16-Sep-2026; no image saved - recommend re-checking live for a screenshot before sending to the vendor. | Root cause: an organisation whose billing period runs into the future but whose stored status had not been updated back to "active" (for example after a payment extended the period) was shown in the table as "Paid - X day(s) left" while being counted in no summary tile at all. That is why Paying read 0 and why the tiles did not add up to the number of organisations. The billing state is now derived from the period itself, so the label and the counter can no longer disagree, and a catch-all bucket ensures every organisation is counted exactly once. Retested: the tiles now account for all 8 organisations. | Also noticed on the same page: two organisations with no plan assigned show "Trial - null day(s)" instead of a proper value (see KAL-005), and two organisations show an identical, very large "342 day(s)" trial remaining (see KAL-006). | Pending
KAL-005 | Platform Admin - Billing | Bug | Medium | P2 | For organisations with no billing plan assigned, the Billing table literally displays "Trial - null day(s)" instead of a sensible message - "null" is an internal programming placeholder that should never be shown to a real user. One other no-plan organisation on the same page correctly shows "Not billed," proving the correct behaviour already exists elsewhere and just isn't applied consistently. | 1. Log in as Platform Admin. 2. Click "Billing". 3. Find an organisation whose Plan column says "None set". 4. Look at that same row's status area - it reads "Trial - null day(s)" instead of a clean message like "Not billed" or a dash. | AI Automation Testing | 2026-09-16 | Fixed | 2026-09-23 | Captured via page text extraction on 16-Sep-2026; no image saved. | Root cause: the server correctly returns "No end date set" for an organisation with no billing end date, but the screen ignored that wording and formatted its own "Trial - {n} day(s)" line, printing the internal placeholder when there was no number to show. The screen now uses the server's wording whenever no end date exists, which is also why the IFQM row already displayed "Not billed" correctly. Retested across all organisation rows: no placeholder text appears. | One other organisation with no plan set ("IFQM" itself) correctly shows "Not billed" instead of the broken text - so the correct behaviour already exists elsewhere in the same feature, it is just not applied consistently to every "no plan" case. | Pending
KAL-006 | Platform Admin - Billing | Clarification | Low | P3 | Two organisations, "TVS Motors" and "Vertex Precision," both show an identical "342 day(s)" trial remaining on the Billing page - an unusually long, suspiciously matching number given the platform's documented default trial length is 14 days. One of the two ("TVS Motors") is even on a paid plan already. This may be leftover test data or a genuine date-calculation issue; flagging for the vendor to confirm. | 1. Log in as Platform Admin. 2. Click "Billing". 3. Find "TVS Motors" and "Vertex Precision" in the table. 4. Compare their Billing column values - both read "Trial - 342 day(s)" with an "Until" date about a year away. | AI Automation Testing | 2026-09-16 | Clarified | 2026-09-23 | Captured via page text extraction on 16-Sep-2026; no image saved. | Investigated as requested. This is not a calculation fault: the trial length is set by hand from the platform console and is permitted to be anything from 0 to 365 days, so 342 days is a value that was entered rather than computed. The two organisations concerned are pre-existing demo records, as IFQM suspected. Because an operator had no way to tell a deliberate extension from a leftover demo value, the billing table now marks any trial running materially longer than the configured trial length, so an unusual value is visible rather than blending in with the ordinary rows. | Flagging for confirmation rather than as a confirmed bug, since these may simply be pre-existing demo/test organisations with manually-set long trial periods. | Pending
KAL-007 | Platform Admin - Support Tickets | Bug | Low | P3 | The Support Tickets page's summary tiles say "Open: 1" and "In Progress: 1," but the visible ticket list (with "Show archived tickets" left unticked, the default) shows none - only 1 closed ticket. The tiles are counting across all tickets including 4 archived ones that stay hidden by default, so the numbers and the visible list disagree, and an admin could believe there's an open ticket needing attention when none is actually visible. | 1. Log in as Platform Admin. 2. Click "Support Tickets". 3. Note the tiles at the top: Total 5, Open 1, In Progress 1, Urgent 0. 4. Leave "Show archived tickets" unticked (the default). 5. Look at the table below - only 1 ticket is listed, and its status is "Closed", not Open or In Progress. | AI Automation Testing | 2026-09-16 | Fixed | 2026-09-23 |  | Confirmed as reported. The summary tiles were counted across every ticket ever raised, while the list below them defaulted to hiding archived tickets, so the two disagreed. The tiles are now counted over exactly the same set the list is showing, so switching "Show archived tickets" updates both together. The Archived count itself remains a total of all time, since it is the figure attached to that switch. Retested: tiles and list agree in both the default and the archived views. | Recommend either making the tiles reflect only what the current filter shows, or clearly labelling them as "across all tickets, including archived". | Pending
KAL-008 | Ideas Workflow - Employee Dashboard | Bug | Low | P3 | After submitting an idea, the confirmation message correctly says "+10 pts earned," but the points total shown next to the user's name in the header doesn't update - it keeps showing the old value until the page is reloaded. The points are correctly recorded in the background; only the on-screen counter fails to refresh itself. | 1. Log in as any employee-level user. 2. Note the current points shown next to your name at the top right (for example "0 pts"). 3. Go to Submit Idea and complete and submit a new idea. 4. Note the confirmation message "+10 pts earned". 5. Without reloading the page, check the points chip at the top - it still shows the old value. 6. Reload the page (or navigate to Dashboard) - it now correctly shows the updated total. | AI Automation Testing | 2026-09-17 | Fixed | 2026-09-23 | Confirmed via before/after check of the page's points-chip value; no dedicated screenshot saved. | Confirmed as reported, and confirmed as cosmetic: the points were always recorded correctly, only the on-screen counter did not refresh. The submission flow now refreshes the signed-in user's details as soon as the confirmation is shown, so the points chip updates without a reload. Retested: the points total moved from 50 to 60 immediately after a submission awarding 10 points. | Minor cosmetic issue - the points are correctly recorded in the background (confirmed correct after reload); this is purely about the on-screen counter not refreshing itself. | Pending
KAL-009 | Ideas Workflow - Organisation Admin Dashboard | Clarification | Medium | P2 | The Organisation Admin's dashboard tells them "1 idea(s) are waiting on your decision," implying they need to approve or reject it - but Organisation Admins are not actually allowed to review ideas anywhere in the app, and opening the idea confirms there's no decision button available ("You cannot review your own idea"). The dashboard's wording promises an action the admin can't actually take. Separately, if nobody in the organisation yet holds an approval-chain role, an idea can end up with no one able to approve it at all. | 1. Log in as an Organisation Admin in an organisation where no employee yet holds an approval-chain role (Immediate Manager / Department Manager / Plant Head). 2. Submit a new idea as that Admin. 3. Go to the Dashboard - note the message "1 idea(s) are waiting on your decision" and the "Review queue (1)" button. 4. Click into Review Queue - note the text explaining administrators do not approve or reject ideas. 5. Open the idea itself - note there is no Approve/Reject option, only Archive, Close and Export, plus the message "You cannot review your own idea". | AI Automation Testing | 2026-09-17 | Fixed | 2026-09-23 |  | Accepted and reworded. The count itself was correct, but the sentence claimed the decision belonged to the administrator, who is deliberately barred from approving or rejecting anything. The dashboard now distinguishes the two cases: a reviewer still reads "N idea(s) are waiting on your decision", while an administrator reads "N idea(s) are awaiting a decision from their reviewers". Archived ideas are also no longer counted, since they are not waiting on anybody. On the related note about an organisation having nobody in an approval role, the system already notifies administrators when an idea reaches a stage nobody holds. | Related note: if nobody in the organisation holds any approval-chain role, the idea has no one who can approve it until a suitable employee is added. Recommend either warning the Admin about this during setup, or adjusting the dashboard wording so it is not implied to be the Admin's decision to make. | Pending
KAL-010 | Login / User Onboarding | Bug | Low | P4 | A brand-new user's first-login "Choose a new password" screen tells them their temporary password "was generated from your name and year of birth" - but the Add User form that created their account never asks for a date of birth. The explanation doesn't match how the account was actually set up. It's purely a wording issue with no effect on security or function, confirmed across three separate first-time logins. | 1. As an Organisation Admin, go to Admin Panel > User List > "+ Add User". 2. Fill in Name, Employee ID, Email, Phone, Role, Department (there is no date-of-birth field anywhere in this form). 3. Save - a temporary password is emailed to the new user. 4. Log in as that new user with the emailed temporary password. 5. Read the forced "Choose a new password" screen's explanation text. | AI Automation Testing | 2026-09-17 | Fixed | 2026-09-23 | Seen in page text during a new manager account's first login, 17-Sep-2026; no image saved. | Confirmed as reported and corrected. The wording was inherited from the bulk-import path, where a temporary password is derived from the name and year of birth; an account created individually through Add User has no date of birth and receives a randomly generated password instead. The first-login screen now reads "a temporary password that was set up for you when your account was created", which is accurate for both routes. Updated in all seven languages. | Purely a wording issue - does not affect security or function. Recommend a generic message such as "a temporary password was generated for you" instead of referencing birth year. Reconfirmed again on 17-Sep-2026 during two more first-time logins (Department Manager and Plant Head test accounts) - same inaccurate wording shown both times. | Pending
KAL-011 | Ideas Workflow - Rejected Ideas List | Bug | Medium | P2 | Right after a manager rejects an idea, their own "Rejected Ideas" page says "No rejected ideas" - as if it never happened. The same idea correctly shows as Rejected everywhere else: the submitter's My Ideas list, the idea's Timeline, and the Organisation Admin's own Rejected Ideas page. The rejection itself is recorded correctly; only this one page, for this one role, fails to show it. | 1. Submit a test idea as any user (for example, an Organisation Admin). 2. Log in as that idea's Immediate Manager (the first-stage reviewer). 3. Open Review Queue, click Review on the pending idea, change Decision to "Reject", add a comment, and submit - confirmation "Decision Submitted" appears and the Review Queue correctly empties. 4. Immediately click "Rejected Ideas" in the left menu, while still logged in as that same Manager - the page says "No rejected ideas." 5. Log out and log back in as the Organisation Admin (or the original submitter) - their own "Rejected Ideas" / "My Ideas" page correctly shows the idea with Status = Rejected, and the idea's Timeline tab correctly shows the Manager's name, timestamp, and rejection comment in full. | AI Automation Testing | 2026-09-17 | Fixed | 2026-09-23 |  | Root cause: this page limits a reviewer to ideas from their own reporting line, and the idea in question had been submitted by the Organisation Admin, who does not report to that Manager. The rejection was recorded correctly, as IFQM observed; it simply fell outside the page's filter. The filter now also includes any idea the viewer has personally acted on, so a reviewer always sees the ideas they have decided. Retested: after rejecting an idea submitted by someone outside their team, the Manager sees it in Rejected Ideas immediately. | The rejection itself is recorded and visible correctly everywhere except this one page for the rejecting Manager's own role. Recommend checking the query/filter used specifically by the Manager-level Rejected Ideas view - it is likely scoped incorrectly (for example, only showing ideas rejected by someone else, or filtering on the wrong reviewer-role field). | Pending
KAL-012 | Roles & Permissions - User Management (Reports To) | Bug | High | P2 | Setting an employee's "Reports To" manager doesn't reliably route their ideas to that manager, and two screens disagree about whether it was even set. The Edit User form shows "- None -" for the manager field, while the Hierarchy tab's Reporting Structure view shows the employee correctly grouped under the intended manager at the very same time. A live test confirmed the Edit User form is right: a fresh idea from that employee landed in the fallback "Manager" role-holder's queue, not the intended manager's - so the Hierarchy tab is silently showing a setup that isn't actually working, giving false confidence to whoever checks it. | 1. As an Organisation Admin, add or edit an employee and set "Reports To" to a specific manager, then save. 2. Open Admin Panel > User List > Edit User for that same employee - note whether "Reports To" shows the manager or "- None -". 3. Separately open Admin Panel > Hierarchy > Reporting Structure and find the same employee - note what manager (if any) they are grouped under there. 4. If the two screens disagree, resolve which one is telling the truth by having that employee submit a brand-new idea and checking which manager's Review Queue it actually lands in. | AI Automation Testing | 2026-09-17 | Fixed | 2026-09-23 |  | Root cause: the Reports To value was always saved correctly; the Edit User dropdown lists only active employees holding a manager-level role, so a manager who is inactive or holds another role had no matching entry and the dropdown fell back to its first option, "- None -". The Hierarchy tab, which reads the stored value directly, was therefore the accurate screen. Edit User now always lists the manager who is actually set, marked "(current)", so the two screens cannot disagree. On routing: the documented behaviour is that an idea follows the reporting line to the nearest holder of the stage's role, and falls back to all holders of that role if the line contains none; the system already notifies administrators when that fallback is used, so the gap is reported rather than silent. Retested: Edit User now shows the assigned manager in every case. | This is more than cosmetic - it silently breaks the documented behaviour ("ideas go to the approver on this line - set it, or the idea is offered to every holder of the role instead") and can misroute real approval decisions to the wrong reviewer. Worse, an admin checking the Hierarchy tab to confirm their setup worked would see a correctly-configured reporting line and have no reason to suspect anything is wrong, when the real routing engine is silently ignoring it. | Pending
KAL-013 | Roles & Permissions - Admin Panel Access Control | Bug | Medium | P2 | A regular Employee-level user has no Admin Panel link in their menu, but typing /admin directly into the browser still loads the full Admin Panel shell - all eight tabs included. The backend correctly blocks the actual privileged data underneath (confirmed via 403 responses on every admin API call), so nothing sensitive is exposed and no unauthorized change actually saves. The problem is purely the front end: instead of an access-denied message, the User List tab just shows an empty "No users yet," which could easily be mistaken for a real (if boring) admin view rather than a blocked one. | 1. Log in as an Employee-level user (for example, one created via Add User with role = Employee). 2. Confirm the left-hand menu has no "Admin Panel" entry. 3. Manually navigate the browser to https://kalpion.ifqm.org.in/admin. 4. Observe the Admin Panel shell (all eight tabs) loads normally. 5. Click "User List" - it shows "No users yet" / "Showing 0-0 of 0" rather than an access-denied message. 6. Click "+ Add User", fill the form, and click Save - the request goes through but the server responds 403 (visible in DevTools Network tab), and no user is actually created. | AI Automation Testing | 2026-09-17 | Fixed | 2026-09-23 |  | Confirmed, including IFQM's observation that the backend authorisation was working correctly throughout. The gap was purely in the browser: no route guard, and an empty list that read like a real but empty admin view. A role check has been added, so any role without administrative rights is redirected away from /admin before the screen loads. Retested as an Employee: navigating directly to /admin now returns to the dashboard, and the admin shell does not render at all. | Backend authorization is working correctly here, which is the important part - this is purely a client-side gap (missing route guard plus a misleading empty-state message instead of a clear "access denied"). Recommend adding a role check that redirects non-admin roles away from /admin entirely, or at minimum shows an explicit permission-denied message instead of a blank/empty admin view. | Pending
KAL-014 | System Settings - API Access Control | Bug | Low | P3 | The /api/settings endpoint hands back the organisation's full internal configuration - SMTP mail server fields, approval-stage internals, and feature flags - to any logged-in user, not just admins, with no 403 returned. This is inconsistent with equivalent admin-only endpoints (like /api/users/admin), which correctly block the same non-admin session. In this test organisation the SMTP fields happened to be blank, so no real mail-server credentials were exposed this time, but the access control gap remains. | 1. Log in as a plain Employee-level user. 2. Open browser DevTools > Network tab. 3. Navigate to any page that triggers a call to /api/settings (the Admin Panel Overview tab works, reachable per KAL-013). 4. Inspect the response - it returns HTTP 200 with the full settings object (SMTP fields, approval_stages, feature flags), not a 403 like /api/users/admin returns for the same session. | AI Automation Testing | 2026-09-17 | Fixed | 2026-09-23 | Confirmed via Network.getResponseBody on the live /api/settings call during an Employee session (Arjun Mehta) - 200 response containing smtp_host/smtp_port/smtp_user/smtp_from, approval_stages, content_protection and idea_screen_protection fields. | Confirmed as reported. The endpoint previously returned the organisation's whole configuration to any signed-in user, removing only the mail password. It now answers non-administrators from an explicit list of the settings the screens genuinely need - the attachment ceiling, the visibility rules, the approval stage names and the feature switches. The mail server host, account, sender and the remaining administrative settings are withheld, and anything added to the configuration in future is private by default rather than public until noticed. Retested as an Employee: 16 permitted settings returned, zero mail or integration fields among them; an administrator still receives the full set. | In this test organisation the SMTP fields happened to be blank, so no real mail-server credentials were exposed this time - but the endpoint's access control should still match the other admin-only endpoints rather than being open to every authenticated user. | Pending
KAL-015 | Insights - Leaderboard | Bug | Low | P3 | The Leaderboard's "Top Scored Ideas" panel, visible to every employee, includes ideas that have been archived or even Rejected, ranked right alongside genuine active ideas - confirmed via the raw API response returning both an archived-but-Approved idea and two archived, already-Rejected ideas in the same top-5 list. This undermines the point of archiving (the app's own confirmation text says archiving "leaves the working lists") and can make withdrawn or rejected work look like it's still being showcased company-wide. | 1. As an Organisation Admin, archive an idea (any status) so it no longer appears in "All Ideas". 2. Separately, have another idea rejected by its reviewer. 3. Log in as any Employee-level user and go to Insights > Leaderboard. 4. Look at the "Top Scored Ideas" panel - both the archived idea and the rejected idea can appear there, ranked by AI score, exactly as if they were active. | AI Automation Testing | 2026-09-18 | Fixed | 2026-09-23 | Confirmed via Network.getResponseBody on /api/leaderboard?period=all during an Employee session (Arjun Mehta) - top_ideas array included IDA-2026-001 (Approved, archived), IDA-2026-002 and IDA-2026-003 (both Rejected, archived) alongside active ideas IDA-2026-005 and IDA-2026-007. | Accepted and corrected. The Top Scored Ideas panel excluded only drafts, so archived and rejected ideas could still be ranked alongside active ones. It now excludes archived and rejected ideas as well, which matches what the Archive confirmation promises. Retested: the panel returns only active, non-archived ideas. | Low severity since this is a ranking/visibility inconsistency rather than a security issue - but it undermines the point of archiving (the app's own Archive confirmation text says archiving "leaves the working lists") and can make withdrawn or rejected work look like it is still being showcased company-wide. Recommend filtering top_ideas to active, non-archived, non-rejected ideas only. | Pending
KAL-016 | Ideas Workflow - Route to Committee | Bug | Critical | P1 | "Route to Committee" is meant to hand a tricky idea to a specific reviewer for a second opinion. It looks like it works - the idea disappears from the original reviewer's queue and the app confirms "Reviewers assigned. Idea routed to committee" - but the newly assigned reviewer never actually receives it in their own Review Queue. The idea is left permanently stuck at "Under Review" with nobody able to approve or reject it: not the original reviewer (removed), not the new one (never received it), and not an Admin (can't review ideas at all, per KAL-009). This makes the feature unusable and destructive in its current state. | 1. Submit a test idea (as any user). 2. Log in as that idea's Immediate Manager (the current stage reviewer) and open Review Queue. 3. Click "Route to Committee" on the idea, search for a specific employee (for example, by typing at least a few letters of their name), select them from the results, and click "Assign Reviewers" - confirmation "Reviewers assigned. Idea routed to committee" appears, and the idea disappears from your own Review Queue. 4. Log out and log in as the person you just assigned - open their Review Queue - it shows "No ideas pending review", the idea is not there. 5. Check the idea's Timeline (from an Admin or the submitter's view) - it shows the idea was routed to committee, is still "Under Review", but no further reviewer action is available to anyone. | AI Automation Testing | 2026-09-18 | Fixed | 2026-09-23 |  | Root cause confirmed as release-blocking, as IFQM recommended. The review queue decided what to show from the organisation's configured approval chain, so an idea routed to a reviewer whose role is not part of that chain left the sender's queue and never appeared in the assignee's - leaving it with no route to a decision. Committee assignments are now handled independently of the chain, since routing to a committee deliberately takes an idea off it. Separately, the person-search in the Route to Committee dialog now lists only people who can actually be routed to and shows their role, so an ineligible choice cannot be made. Retested end to end: the assignee receives the idea, it leaves the sender's queue, and the assignee can record a decision. | This effectively makes the "Route to Committee" feature unusable and destructive in its current state - any idea routed this way becomes permanently stuck with no path to Approved or Rejected, since the assigned reviewer(s) never actually receive it to act on. Recommend treating this as release-blocking for the feature until the assigned reviewer(s) genuinely receive the idea in their Review Queue. | Pending
KAL-017 | Ideas Workflow - Idea Board Sorting | Bug | Medium | P2 | Choosing "Sort: Newest" on the Idea Board doesn't actually order ideas by submission date. Checked against the raw API response, an idea with more votes was returned first regardless of its actual creation timestamp - the two zero-vote ideas were correctly ordered by date between themselves, but the more-voted idea jumped ahead of a genuinely newer one. The "newest" sort parameter appears to be silently ignored, falling back to a vote-based order instead. The "Sort: AI Score" option was checked separately and worked correctly, so this looks specific to the "newest" case. | 1. On the Idea Board, upvote one idea that was submitted earlier than another idea that has zero votes. 2. Switch the sort dropdown to "Sort: Newest". 3. Open the browser's Network tab and inspect the response from /api/votes/board?sort=newest - compare the created_at field of each idea against the order they are returned in. 4. The upvoted idea appears first even though a different idea has a later created_at timestamp. | AI Automation Testing | 2026-09-18 | Fixed | 2026-09-23 | Confirmed via Network.getResponseBody on /api/votes/board?sort=newest - raw JSON showed created_at "2026-09-17 04:46:46" (IDA-2026-007, 1 upvote) returned before created_at "2026-09-17 04:47:09" (IDA-2026-008, 0 upvotes), even though the second idea was submitted later. | Root cause: the screen sends "newest" but the server recognised only "recent", so the value was silently ignored and the query fell back to the vote order - exactly as IFQM deduced from the API response. Both spellings are now accepted, so a page cached with either value works. AI Score sorting was unaffected, as observed. Retested: with "Sort: Newest" selected, all 20 board ideas are returned in descending date order. | The "Sort: AI Score" option was checked in the same session and worked correctly (ideas ordered by ai_score descending), so this appears specific to the "newest" sort case in the backend query, not a general sorting failure. | Pending
KAL-018 | Admin Panel - Hierarchy Configuration | Clarification | Medium | P2 | Adding or removing an approval stage in Admin Panel > Hierarchy and saving immediately changes the stage count for every idea already mid-review, with no warning shown. An idea sitting at "Department Manager 2/3" (its last stage) instantly became "2/4" the moment a fifth stage was added and saved, extending what its submitter and reviewers were expecting - and correctly reverted once the stage was removed again. This live-recalculation behaviour may be intentional, but there's no confirmation dialog warning the admin that saving will affect ideas currently in progress. | 1. Confirm an idea is currently sitting partway through review (for example, "Department Manager 2/3" in a reviewer's Review Queue). 2. As an Organisation Admin, go to Admin Panel > Hierarchy, use "Add a stage..." to add a new stage, and click "Save Workflow" - a plain "Approval workflow saved" message appears, with no mention of any effect on ideas already in progress. 3. Check the same idea's Review Queue entry again - its stage counter has changed (for example, to "2/4") to reflect the new, longer chain. 4. Remove the added stage and save again - the counter correctly reverts (confirmed reversible in this test). | AI Automation Testing | 2026-09-18 | Clarified | 2026-09-23 |  | Reviewed as a clarification. The behaviour is intentional: the approval chain is read live rather than frozen at submission, so that a correction to the chain reaches the ideas it was made for. Freezing each idea's chain would mean a mistake in the configuration could never be repaired for work already in progress. IFQM's point that it can surprise an administrator is accepted, and a confirmation has been added: saving the workflow while ideas are part-way through it now states how many are affected and warns that a stage may be added to or removed from what they still have to pass. | Filed as a Clarification rather than a straight Bug since the underlying behaviour (recalculating live rather than freezing at submission time) is a legitimate design choice, not obviously wrong - but it can catch an admin by surprise (an idea one approval away from being finished can suddenly need an extra sign-off) and there is no confirmation dialog warning that saving the workflow will affect ideas already mid-review. Recommend at least warning the admin when saving a hierarchy change while ideas are currently in progress. | Pending
KAL-019 | Ideas Workflow - Submit Idea (Attachments) | Bug | Medium | P2 | Attaching a disallowed file type to an idea is accepted with no warning when selected, then correctly rejected by the server at submit time (/api/upload returns 400) - but the idea itself still submits successfully with the normal "+10 pts earned" confirmation, and the user is never told their attachment didn't attach. The only way to discover it failed is to open the idea later and see "No attachments." By contrast, an oversized file is caught immediately at selection with a clear on-screen message before any upload is attempted - the file-type check has no equivalent warning. | 1. Start Submit Idea and reach the Attachments step (optional Supporting Document fields for Situation/Solution). 2. Attach a file with a disallowed extension - the file picker's own filter can be bypassed (for example, dragging the file in, or via automation that sets the input's files directly). 3. Complete the remaining steps and click Submit New Idea - the confirmation reads "Idea #IDA-... submitted! +N pts earned" with no mention of any attachment problem. 4. Open the newly created idea and check its Attachments tab - it reads "No attachments," confirming the file never actually saved. 5. For comparison, repeat with a file exceeding the 10 MB size limit - this one is caught immediately at selection with a clear on-screen message, before any submission is attempted. | AI Automation Testing | 2026-09-18 | Fixed | 2026-09-23 |  | Confirmed, including IFQM's observation that server-side validation was working correctly and nothing unsafe was stored. Two changes were made. A disallowed file type is now refused at the moment it is selected, with the same clear message an oversized file already produced, so the problem is visible before the form is completed. And if an upload still fails at submission, the failure is now reported on the confirmation instead of being discarded, naming the file that did not attach. Retested: a .exe file is refused at selection and rejected by the server, while a .pdf uploads normally. | Server-side type validation is working correctly (400 on the disallowed type), so nothing unsafe is actually stored - this is purely a silent-failure UX gap. Recommend either validating file type client-side the same way file size already is, or surfacing the /api/upload failure as a visible warning on the submit confirmation instead of reporting a clean success. | Pending
KAL-020 | Ideas Workflow - Archiving vs Review Queue | Bug | High | P2 | Archiving an idea is supposed to take it out of everyone's working lists - the app's own confirmation message says archiving "leaves the working lists" - but it doesn't remove the idea from a reviewer's Review Queue. An archived idea still appears there with a fully working Review button, and opening it opens the normal Approve/Reject dialog with no indication anywhere that the idea has been archived. This means a decision can still go through on an idea the organisation had already set aside. | 1. As the current stage reviewer for a pending idea, note it in your Review Queue. 2. As an Organisation Admin (or the submitter), open that same idea and click Archive - confirm it now appears under All Ideas > "Archived only" rather than the normal list. 3. Log back in as the reviewer and open Review Queue - the idea is still listed, with Route to Committee / View / Review all present. 4. Click Review - the normal Review/Decide dialog opens, fully able to Approve or Reject, with no mention that the idea has been archived. | AI Automation Testing | 2026-09-18 | Fixed | 2026-09-23 |  | Confirmed as reported. Archiving removed an idea from the browse lists but not from the review queue, so a decision could still be recorded on work the organisation had set aside. Archived ideas now leave the review queue, and any attempt to approve or reject one is refused with an explanation, including a direct request made outside the screen. Retested: the archived idea disappears from the reviewer's queue and a decision attempt is refused. | This weakens the point of archiving considerably - anything archived mid-review can still be approved or rejected by whoever happens to hold it, which could let a decision go through on an idea the organisation had already decided to set aside. Recommend either blocking review actions on archived ideas, or removing them from the Review Queue entirely once archived. | Pending
KAL-021 | Ideas Workflow - Co-Suggesters | Bug | Medium | P2 | An employee listed as a co-suggester on an idea isn't blocked from later reviewing and approving that same idea, if they happen to be the assigned reviewer at whatever stage it reaches. Confirmed live: a co-suggester's Review Queue showed the idea as a normal actionable item with no conflict-of-interest warning, and their approval went through normally. The original submitter is already blocked from reviewing their own idea ("You cannot review your own idea") - the same protection was never extended to co-suggesters. | 1. Submit an idea and add a specific employee as a co-suggester during the Co-Suggesters step. 2. Ensure that same employee is the Immediate Manager (or other stage) reviewer who would normally receive this idea. 3. Log in as that employee and open Review Queue - the idea appears as a normal actionable item. 4. Click Review and Approve (or Reject) - the action succeeds with no warning about the co-suggester relationship. | AI Automation Testing | 2026-09-18 | Fixed | 2026-09-23 | Confirmed via the Review/Decide dialog for IDA-2026-014 opening normally for Manoj Manager (a listed co-suggester) with no conflict warning, and the subsequent /api/ideas/review-action call returning 200 for his approval. | Accepted and corrected. The protection that stops an author reviewing their own idea was never extended to the people named alongside them. A co-suggester is an author of the idea, so the same rule now applies: the idea does not appear in their review queue, and a decision is refused if attempted directly. Both the current co-suggester records and the older two-slot fields are checked, so ideas created before the newer structure are covered. Retested: an idea naming the reviewer as co-suggester is absent from their queue and a decision is refused. | The same self-review protection already exists for the original submitter ("You cannot review your own idea") - recommend extending an equivalent block or at least a warning to co-suggesters reviewing an idea they contributed to. | Pending
KAL-022 | Ideas Workflow - Co-Suggesters (Data Model) | Clarification | Low | P3 | The Submit Idea form lets you add three or more co-suggesters with no limit warning, and the on-screen Review step correctly lists everyone added. But the underlying idea record keeps two different, disagreeing copies of the co-suggester list: older co_suggester_1_id/co_suggester_2_id fields that only capture the first two people, and a separate, complete co_suggesters array. No user-facing symptom was found in this session, but anything still reading from the older two-slot fields would silently lose the third co-suggester onward. | 1. Submit an idea and add three co-suggesters via the Co-Suggesters step (the UI allows this with no limit warning). 2. Complete and submit the idea. 3. Inspect the idea's raw API response (for example /api/ideas/{id}) - note that co_suggester_1_id and co_suggester_2_id hold only the first two added, while the co_suggesters array and co_suggesters_display field correctly list all three. | AI Automation Testing | 2026-09-18 | Fixed | 2026-09-23 | Confirmed via the raw /api/ideas/14 response: co_suggester_1_id=5 (Kavita), co_suggester_2_id=7 (Sunita), with no field for the third - while co_suggesters correctly listed all three (ids 5, 7 and 2/Manoj) and co_suggesters_display read "Kavita Rao, Sunita Verma, Manoj Manager". | Investigated as the latent risk IFQM identified, and a real user-facing effect was found that had not been observed in testing: because the older two-slot fields hold only the first two co-suggesters, any list scoped on those fields hid the idea from a third or later co-suggester - meaning they could not see an idea they were named on. Every place that asks whether a person is connected to an idea now reads the complete co-suggester record as well as the two legacy fields. Retested with three co-suggesters: the third is correctly recognised as an author of the idea. The duplicate storage is retained for now for compatibility with older records. | Filed as a Clarification since no directly observable user-facing symptom was found in this session (the on-screen display and Review step both correctly showed all three) - but this is worth the vendor's attention as a latent risk: any current or future code path reading the legacy two-slot fields (for example, points-sharing or notifications, neither confirmed either way in this session) would silently miss the third co-suggester onward. | Pending
KAL-023 | Roles & Permissions - User Management (Remove/Deactivate) | Bug | High | P2 | Removing a user who has submitted ideas is handled gracefully - the app deactivates them instead of deleting, with a clear message explaining why. But removing a user who has instead reviewed or approved other people's ideas throws a raw, unhandled server error (500) instead of that same graceful treatment, reproduced twice against the organisation's Plant Head. The submitted-ideas case shows the vendor already has the right pattern for this; the reviewer/approval-history case looks like it was simply missed. | 1. As an Organisation Admin, identify a user who has approved or rejected at least one idea (visible in that idea's Timeline as a reviewer action). 2. Go to Admin Panel > User List and click Remove on that user's row. 3. Observe "Server error. Please try again." and the underlying request returning 500. 4. For comparison, click Remove on a user who has only submitted ideas of their own (never reviewed anyone else's) - this correctly deactivates them with a clear message. 5. For further comparison, click Remove on a brand-new user with no idea-related history at all - this correctly and fully deletes them with a clear message. | AI Automation Testing | 2026-09-18 | Fixed | 2026-09-23 |  | Root cause confirmed, and IFQM's reading was correct - the safety net existed but did not cover this case. Removing a user is blocked by two kinds of history, not one: ideas they submitted, which was handled, and entries in the approval trail for ideas they reviewed, which was not. The second raised a database constraint error that surfaced as an unexplained server error. Reviewer history is now treated exactly like authorship: the account is deactivated rather than deleted, with a message saying why, so the audit trail keeps the name attached to each decision. A catch-all was also added so that any future reference degrades to deactivation rather than an error. Retested on a user with approval history: the account is deactivated with a clear message. | The submitted-ideas case shows the vendor already has the right pattern for this (deactivate instead of delete, explain why) - this looks like the reviewer/approval-history case was simply missed when that safety net was built, rather than a design gap. Recommend extending the same deactivate-with-reason handling to cover reviewer/approval history. | Pending
KAL-024 | Roles & Permissions - User Management (Edit User) | Bug | Medium | P2 | Opening Edit User on an existing employee shows the Phone field as blank, even for a user confirmed to have a real saved phone number. Because Phone is a required field, this silently blocks saving any other change (like just switching someone back to Active) unless the admin happens to already know and retypes that person's phone number - the form gives no other clue why the save is failing. | 1. As an Organisation Admin, open Admin Panel > User List and click Edit on any existing employee who has a phone number on file. 2. Check the Phone field - it is empty rather than showing their saved number. 3. Try changing an unrelated field (for example, Status) and click Save Changes - nothing happens and no request is sent, with no visible error explaining that the (invisible, blank-looking) Phone field is what's blocking the save. 4. Manually type the person's actual phone number into the Phone field and click Save Changes again - this time it saves successfully. | AI Automation Testing | 2026-09-18 | Fixed | 2026-09-23 | Confirmed via direct read of the uf-phone form field's value (empty) immediately after opening Edit User on Priya BulkTest, a user confirmed to have been created with phone 9876500021 via Bulk Import; the Save Changes click produced no API call at all until the phone field was manually re-filled. | Root cause: the user list sent to the Edit User form did not include the phone number at all, so the required field was always blank and blocked saving until the administrator retyped the number from memory - exactly the operational cost IFQM described. The phone number is now returned with the user record and the form opens with it filled in. Retested: opening Edit User on an existing employee shows their saved number, and unrelated changes such as reactivation save without further input. | This has a real operational cost: an admin trying to make an unrelated change (like reactivating someone) can be silently blocked with no clear cause, and can only work around it by already knowing that person's phone number from memory or another source. Recommend fixing the Edit User form to correctly load and display the user's existing phone number. | Pending
KAL-025 | Ideas Workflow - Drafts | Bug | Medium | P2 | An idea saved as a Draft - never actually submitted - appears in the Organisation Admin's "All Ideas" list right alongside genuinely submitted ideas, labelled "Draft." But that same page's own status filter has no "Draft" option to filter by, which suggests drafts were never meant to show up there at all. A regular Employee's own "All Ideas" view is correctly scoped to just their own ideas, so this is specifically about admin-level visibility into other people's unfinished drafts. | 1. As any user, go to Submit Idea, fill in the required Situation and Solution fields, and click through to the Review & Submit step. 2. Click "Save Draft" instead of "Submit New Idea" - confirmation "Draft saved! Idea code: IDA-..." appears. 3. Log in as an Organisation Admin and open All Ideas - the draft appears in the list with Status "Draft". 4. Check the status filter dropdown on the same page - it offers All Statuses, Submitted, Under Review, Approved, Rejected and Implemented, but no "Draft" option. | AI Automation Testing | 2026-09-18 | Fixed | 2026-09-23 | Confirmed via page text: Admin's All Ideas list showing "IDA-2026-016 ... Draft ... View" alongside submitted ideas, while the same page's status filter chips list only All Statuses/Submitted/Under Review/Approved/Rejected/Implemented with no Draft option; separately confirmed an unrelated Employee's own All Ideas view is correctly scoped to only their own idea, not showing this or anyone else's ideas. | Accepted, and resolved in the direction IFQM's remark implied. A draft has not been submitted to anybody, so it now appears only to its own author; other people's drafts no longer appear in the Organisation Admin's All Ideas list. The matching "Draft" filter option has also been added, so an author can filter for their own unfinished work. Retested: a draft raised by an employee is invisible to the administrator and visible to its author under the new filter. | Filed as a Bug rather than a Clarification specifically because of the missing filter option - if admin visibility into drafts were the intended design, a matching filter option would be the expected companion. Recommend either excluding draft-status ideas from the Admin All Ideas list entirely, or adding a proper "Draft" filter option if this visibility is in fact intentional. | Pending
KAL-026 | Ideas Workflow - Drafts | Bug | High | P2 | There's no way anywhere in the app to resume, edit, or complete an idea saved as a Draft. Clicking Submit Idea again just opens a blank new form with no mention of the pending draft, and opening the draft itself only offers Archive, Close, and Export PDF - no Edit or Continue button. The draft's data is safely saved, but once saved it's a permanent dead end; the only way to actually get it in front of a reviewer is starting over from scratch. Separately, the draft's own detail view mislabels it "Submitted on [date]" even though it was never submitted. | 1. Start Submit Idea, fill in the required fields, and click "Save Draft" at the Review & Submit step - confirmation "Draft saved! Idea code: IDA-..." appears. 2. Go to My Ideas and open ("View") that draft - the detail modal is read-only, offering only Archive, Close and Export PDF. 3. Go back to Submit Idea and start a new one - it opens a completely blank Step 1 form, with no mention of the existing draft or any option to resume it. | AI Automation Testing | 2026-09-18 | Fixed | 2026-09-23 |  | Confirmed as a genuine gap in core functionality. The ability to reopen and complete a saved draft already existed in the system but nothing in the interface linked to it, so a draft was unreachable once saved. A "Continue editing" action has been added to the draft's own row in My Ideas and to its detail view, both of which reopen the draft in the submission form with its saved content. The detail view also now reads "Created on" rather than "Submitted on" while an idea is still a draft. Retested: a saved draft reopens with its content intact and submits normally. | This is a real gap in a core piece of functionality, not a cosmetic issue - the feature exists, successfully persists data, and is discoverable, but has no path to completion. Recommend adding either an Edit/Continue action on the draft's own detail view, or a "Resume draft" prompt on the Submit Idea page when a draft already exists. Also recommend relabelling "Submitted on" to something like "Created on" or "Last saved on" for ideas still in Draft status. | Pending
KAL-027 | Ideas Workflow - All Ideas Search | Bug | Low | P3 | The "Search ideas..." box on All Ideas only matches an idea's title, solution text, and idea code - not the Submitted By or Department columns, even though both are shown as prominent columns in the same table. Searching a real submitter's name or a real department with active ideas can return "No ideas found," which could easily be misread as meaning that person or department has never submitted anything. | 1. On All Ideas, note a real submitter's name from the "Submitted By" column (for example, "Sunita Verma", who has submitted a genuine idea). 2. Type just that name into the "Search ideas..." box - it returns "No ideas found. Submit your first idea!" 3. Separately, type a real department name from the "Department" column that does not happen to appear in any idea's title or solution text (for example, "Production") - same empty result. | AI Automation Testing | 2026-09-18 | Fixed | 2026-09-23 | Confirmed via the underlying /api/ideas?search=Sunita and /api/ideas?search=Production calls both returning zero results (200, empty list), while /api/ideas?search=compressor and /api/ideas?search=IDA-2026-008 (title text and idea code respectively) both correctly returned matches. | Accepted and extended. The search covered the title and idea code only. It now also matches the Submitted By and Department columns, both of which are visible in the same table and were reasonably expected to be searchable. Retested: searching a submitter's name and searching a department each return their ideas rather than an empty result. | Low severity since title/code search does work correctly and this is a scope gap rather than a broken feature - but worth extending the search to also match Submitted By and Department, since both are visible, expected-searchable columns in the same table. | Pending
KAL-028 | My Profile - Phone Number Change (OTP) | Bug | High | P2 | Typing the wrong confirmation code while changing your phone number on My Profile doesn't show a normal "wrong code, try again" message - it fully logs the user out and dumps them on the public marketing homepage instead. Logging back in shows no real damage was done (the phone number correctly stayed unset), but a routine, easily-made typo shouldn't cost the user their entire session. Separately noticed: the code-entry field's placeholder says "6-digit code" but its maxlength is set to 8. | 1. Log in and go to My Profile. 2. Click "Change" next to Phone, enter any phone number, and click "Send code" - confirmation "Code sent to the new number" appears and a code-entry field replaces the phone field. 3. Enter an incorrect 6-digit code (for example, 000000) and click Confirm. 4. Observe that instead of an inline error, the browser ends up at the public kalpion.ifqm.org.in marketing homepage, fully logged out. 5. Log back in - the account is intact and the phone field correctly remains unset. | AI Automation Testing | 2026-09-18 | Fixed | 2026-09-23 |  | Root cause: an incorrect code was answered with an authentication error, and the browser treats any such response on a signed-in request as the session having expired, which is why it cleared the session and returned to the public homepage. Two changes were made. The server now answers an incorrect code as a bad request rather than an authentication failure, which is what it is on a signed-in screen. And the browser now only ends a session when the server explicitly says the session has expired, which protects every other verification step in the product from the same effect. The code field's maximum length has also been corrected from 8 to 6 to match its label. Retested: an incorrect code returns an inline error and the session remains active. | Separately noticed while testing this: the code-entry field's placeholder reads "6-digit code" but its maxlength is set to 8, not 6 - a minor, low-stakes inconsistency worth a quick look while this area is being fixed. The main issue is more serious than a cosmetic bug - a routine, easily-made mistake (mistyping a code) should never cost the user their entire session. | Pending
KAL-029 | Login - Sign in with a Code (Passwordless OTP) | Bug | High | P2 | Repeatedly clicking "Send me a code" / "Resend code" on the passwordless login screen each returns a successful response (200) - the UI even correctly starts its own resend cooldown each time, proving the click genuinely registered - but no new email ever arrives. Across three separate, deliberately spaced-out attempts, the inbox kept showing the same single original code, which then fails verification every time. This blocks passwordless login entirely for the account, though signing in with a password still works as a fallback. | 1. On the Kalpion login page, click "Sign in with a code instead". 2. Enter a valid account's username/email (for example, kalpion.qafreshtest@yopmail.com) and click "Send me a code" - confirmation "If that belongs to an account, a code has been sent to it." appears. 3. Check that account's email inbox and note the sign-in-code email's timestamp and 6-digit code. 4. Wait for the on-screen "Resend in Ns" cooldown to fully clear, then click "Resend code" - the same 200 success response and a fresh cooldown timer appear. 5. Check the inbox again - no new email has arrived; it is still the same single email with the same code and timestamp as before. 6. Enter that code and click "Verify and sign in" - it fails with "Incorrect code. N attempt(s) remaining." | AI Automation Testing | 2026-09-18 | Fixed | 2026-09-23 |  | Root cause identified, and it explains both halves of what IFQM observed. Each request generated a new code and immediately invalidated the previous one, before any attempt to deliver it - and the endpoint reported success whether or not delivery actually happened. So a failed resend silently destroyed the only working code while the screen showed success and started its cooldown, leaving no way to obtain a usable code. The existing code is now retired only after the replacement has genuinely been sent, a failed delivery discards the unusable new code and reports the failure instead of a false success, and exactly one live code per account is maintained throughout. Retested: a successful resend retires the previous code and issues a working one. | This fully blocks the passwordless "Sign in with a code" feature end-to-end for the account tested - a user has no way to obtain a working code through the UI, though signing in with a password remains available as a fallback. Recommend checking the actual outbound email delivery path for the OTP-request endpoint specifically (as opposed to just the API's own success response), since the endpoint itself is answering successfully while the email side effect appears not to be happening. | Pending